HK Flu Ensemble (HK-FluEns)

Planning, Architecture & Implementation Roadmap

Hong Kong Influenza Forecasting Network — Pre-Implementation Assessment

Prepared for: Parth Singh   |   Date: March 2026   |   Status: Planning Phase

# 1. Executive Summary

This document provides the full pre-implementation planning package for HK-FluEns, a Hong Kong influenza forecasting network modelled structurally on the CDC FluSight network but adapted to Hong Kong's unique epidemiological, climatic, and data-infrastructure context. It covers four deliverables: (1) an assessment of the existing codebase in Flu_Forecast_HK_2026-27_Updated_20260318; (2) a phased implementation roadmap with realistic timelines and dependencies; (3) a complete system architecture; and (4) a risk register with mitigations and open decision points that must be resolved before coding begins.

The existing project is a well-structured practicum pipeline producing a three-model ensemble (SARIMA + ETS(A,A,A) + Historical Benchmark) for a narrative review paper. It represents a strong analytical foundation. However, transitioning it to HK-FluEns requires substantial architectural expansion: moving from a single-researcher script pipeline to a hub-and-spoke forecasting network with standardised probabilistic output, automated data ingestion, and a governance structure for multi-institutional participation.

⚠ Critical Finding: Key finding: Two of eight scripts (07-ensemble_model.py and 08-ensemble_evaluation.py) are fully production-quality and directly reusable. Scripts 01-06 are stub files — their outputs exist in the repository but the implementation code was not committed. These stubs must be reconstructed as the foundation of Phase 0.

# 2. Existing Code Assessment

The folder Flu_Forecast_HK_2026-27_Updated_20260318 contains 8 numbered scripts, processed and raw data, model outputs, figures, and documentation. The assessment below examines each component and renders a verdict of Retain, Modify, or Rebuild.

## 2.1  What Exists — Inventory Summary

| Component | Description | Status |
| --- | --- | --- |
| scripts/01_data_preparation.py | Loads CHP Excel, computes ILI+, COVID gap fill, log-transform | STUB — outputs exist, code not committed |
| scripts/02_stationarity_acf_pacf.py | ADF test, ACF/PACF, order selection | STUB — figures exist, code not committed |
| scripts/03_model_fitting.py | Fits 9 SARIMA candidates, selects by AIC/BIC | STUB — model_coefficients.json exists |
| scripts/04_residual_diagnostics.py | Ljung-Box, Shapiro-Wilk, 2×2 diagnostic panel | STUB — figures exist |
| scripts/05_forecast_generation.py | Bootstrap PI (n=600), 78-/104-week forecast | STUB — forecast CSVs exist |
| scripts/06_figures_and_narrative.py | Publication figures, narrative text generation | STUB — figures exist |
| scripts/07_ensemble_model.py | ETS(A,A,A) from scratch, 3-model ensemble, strain multiplier | FULLY IMPLEMENTED — production quality |
| scripts/08_ensemble_evaluation.py | Rolling-origin CV, acceptance criterion, bar charts | FULLY IMPLEMENTED — production quality |
| data/raw/raw_chp_weekly.xlsx | CHP Weekly Influenza Surveillance 2014-2026 | RETAIN — primary data source |
| data/raw/raw_flunet_hk.csv | WHO FluNet Hong Kong 1997-2026 | RETAIN — valuable historical depth |
| data/processed/processed_master_dataset.csv | 636 weeks × 55 columns: merged CHP + FluNet + HKO | HIGH VALUE — retain, update automatically |
| data/processed/processed_model_ready.csv | 373 weeks (2019-2026), log-transformed, regressors | RETAIN — starting point for model training |
| data/processed/processed_covid_imputed_series.csv | COVID gap (Apr 2020-Sep 2022) filled by seasonal decomp + Kalman | RETAIN with caveat — MAPE 76.3% |
| outputs/forecasts/forecast_78wk_2026_27.csv | SARIMA: 78-week forecast + 80%/95% PI | MODIFY — reformat to FluSight quantile spec |
| outputs/coefficients/model_coefficients.json | SARIMA(1,0,1)(1,1,0)[52] fitted parameters | RETAIN as reference baseline |
| documentation/Model_Card_v2.0_Supervisor_Package.docx | Original model card | SUPERSEDED by this document |

## 2.2  Critical Technical Findings

### Finding 1: Stub Scripts Are the Highest-Priority Rebuild Task

Scripts 01-06 contain only module docstrings and 2-3 lines of import/stub code. The actual pipeline logic — data loading, COVID imputation, SARIMA fitting, bootstrap forecast generation — was run interactively and the outputs committed, but the code was not saved. This is the single most important gap: without reproducible scripts 01-06, the pipeline cannot be re-run on updated data or shared with contributors.

### Finding 2: Target Variable Requires Standardisation

The current target is ILI+ = ILI_FMC_rate × positivity_rate — a synthetic composite unique to this project. FluSight's primary target is wILI% (weighted influenza-like illness percentage from sentinel physicians). Hong Kong's CHP reports both ILI per 1,000 consultations (GOPC rate) and laboratory positivity separately. For HK-FluEns, a formal target definition must be agreed before implementation, since all model evaluation, ensemble combination, and hub submission formats depend on a consistent target.

### Finding 3: Climatological Regressors Are a Limitation

The ARIMAX regressors (temperature, absolute humidity) are drawn from HKO 30-year climatological normals (1991-2020), not actual weekly observed weather. This means the model cannot respond to anomalous weather conditions — a known mechanistic driver of influenza transmission in subtropical climates. For HK-FluEns, actual weekly AH data should replace climatological proxies.

### Finding 4: Bimodal Seasonality Is Partially Addressed

The SARIMA(1,0,1)(1,1,0)[52] model applies a single seasonal differencing at lag 52. This captures the annual cycle but does not explicitly model the bimodal structure (winter Jan-Mar, summer Jun-Aug). The Historical Benchmark component partially compensates by encoding pre-pandemic bimodal week-by-week medians, but no model in the ensemble has a formal two-peak seasonal decomposition. A regime-switching or two-component seasonal model is needed for HK-FluEns.

### Finding 5: Output Format Is Not FluSight-Compatible

The current forecast output contains only the point forecast plus 80%/95% prediction interval bounds. The FluSight format requires 23 quantiles per forecast horizon (0.01, 0.025, 0.05, 0.10, ..., 0.95, 0.975, 0.99) plus the point estimate, for each of 1-4 forecast horizons. The bootstrap draws already exist in the pipeline but are not currently saved as quantile outputs.

### Finding 6: Equal Weights vs. AWBE

The current ensemble uses fixed equal weights (1/3 each). The project brief specifies an Adaptive Weight Blending Ensemble (AWBE) that re-weights based on recent performance. This requires implementing the AWBE algorithm and tracking per-model performance windows — a significant engineering addition.

### Finding 7: COVID Imputation Quality

The imputed COVID-gap series (Apr 2020-Sep 2022, 54 weeks) was validated using pseudo-validation MAPE of 76.3% — indicating the imputed values have large uncertainty. While imputation is necessary for continuity, models trained on imputed data should include sensitivity analyses with and without the imputed period.

## 2.3  Asset Classification — Retain / Modify / Rebuild

| Asset | Decision | Rationale |
| --- | --- | --- |
| processed_master_dataset.csv (55 cols) | RETAIN | Extensive feature engineering; 636 weeks of merged data is the most valuable asset in the project |
| raw_chp_weekly.xlsx + raw_flunet_hk.csv | RETAIN | Primary data sources; form the basis of all historical training data |
| ETS(A,A,A) implementation (script 07) | RETAIN | Clean, dependency-free scipy implementation; correctly handles bimodal seasonality; well-tested |
| Rolling-origin CV framework (script 08) | RETAIN | Acceptance criterion logic and multi-window design are reusable; add WIS scoring |
| Historical percentile benchmark concept | RETAIN | Effective magnitude anchor; reuse as one ensemble component |
| SARIMA implementation approach | RETAIN | From-scratch scipy approach avoids version fragility; retain pattern for HK-FluEns SARIMA |
| Strain multiplier table (H3N2/H1N1/B) | RETAIN | Derived from FluNet ratios; valid for operational use; extend with uncertainty |
| COVID suppression flags and logic | RETAIN | Correctly identifies 54 suppressed weeks; needed for any future structural break handling |
| Forecast output format (point + 80/95 PI) | MODIFY | Extend to 23-quantile FluSight format by saving bootstrap quantiles at each horizon step |
| Ensemble equal weights (1/3 each) | MODIFY | Replace with AWBE; keep equal-weight version as initialiser and fallback |
| Climatological weather regressors | MODIFY | Replace with actual weekly HKO observed data; maintain z-score normalisation |
| Scripts 01-06 (all stubs) | REBUILD | Must be fully reconstructed from pipeline logic; use outputs + model_coefficients.json to reverse-engineer |
| ETL / data ingestion pipeline | REBUILD | Currently manual Excel import; need automated CHP scraping + FluNet API + HKO feed |
| Hub architecture and submission spec | REBUILD | Does not exist; must be designed from scratch using FluSight as structural template |
| Probabilistic quantile forecasting | REBUILD | Need to add quantile extraction from bootstrap draws across all 4 forecast horizons |
| WIS scoring and wave-stratified evaluation | REBUILD | Currently only MAE/RMSE; WIS is the FluSight primary metric |
| AWBE algorithm | REBUILD | Not yet implemented; requires sliding window performance tracking and weight solver |
| Novel data streams (wastewater, travel, school) | REBUILD | Not currently in pipeline; requires new ETL connectors and model integration |

# 3. System Architecture

HK-FluEns follows a hub-and-spoke architecture with four logical layers: Data Infrastructure, Model Layer, Hub/Ensemble Layer, and Distribution Layer. The diagram below describes the components, data flows, and interfaces between modules.

## 3.1  Architecture Overview (Text Diagram)

┌──────────────────────────────────────────────────────────────────────────┐
│                        DATA INFRASTRUCTURE LAYER                         │
│                                                                          │
│  ┌─────────────────┐  ┌──────────────────┐  ┌───────────────────────┐   │
│  │  CHP Flu Express │  │  WHO FluNet API   │  │  Novel Data Streams   │   │
│  │  (PDF → ETL)     │  │  (weekly pull)    │  │  ┌───────────────┐   │   │
│  │  · ILI rates     │  │  · strain counts  │  │  │ Wastewater    │   │   │
│  │  · positivity    │  │  · positivity     │  │  │ HKO weather   │   │   │
│  │  · age groups    │  │  · specimens      │  │  │ School term   │   │   │
│  └────────┬─────────┘  └────────┬──────────┘  │  │ Travel (HK-M) │   │   │
│           │                     │              │  └───────────────┘   │   │
│           └──────────┬──────────┘              └──────────┬───────────┘   │
│                      ▼                                     ▼               │
│              ┌────────────────────────────────────────────────────┐        │
│              │           Master Dataset Store                     │        │
│              │   processed_master_dataset.csv → versioned DB      │        │
│              │   · 55+ columns, weekly, 2014-present              │        │
│              │   · COVID gap flagged + imputed                     │        │
│              │   · Standardised ISO week indexing                  │        │
│              └──────────────────────────┬─────────────────────────┘        │
└─────────────────────────────────────────┼────────────────────────────────┘
                                          │
┌─────────────────────────────────────────┼────────────────────────────────┐
│                          MODEL LAYER    │                                 │
│                                         ▼                                 │
│  ┌──────────────────┐  ┌───────────────────────┐  ┌───────────────────┐  │
│  │  Model A          │  │  Model B               │  │  Model C          │  │
│  │  SARIMA(1,0,1)    │  │  ETS(A,A,A)            │  │  Gradient Boost   │  │
│  │  (1,1,0)[52]      │  │  + bimodal seasonal    │  │  (XGBoost/LightGB)│  │
│  │  + AH + temp      │  │  correction            │  │  + novel streams  │  │
│  │  Statistical      │  │  Statistical           │  │  ML               │  │
│  │  baseline         │  │  adaptive              │  │  feature-rich     │  │
│  └────────┬──────────┘  └──────────┬─────────────┘  └────────┬──────────┘  │
│           │                        │                          │              │
│     Each model produces:           │                          │              │
│     · 23-quantile forecast          │                          │              │
│     · per horizon (1,2,3,4 wk)     │                          │              │
│     · FluSight submission CSV      │                          │              │
└───────────┼────────────────────────┼──────────────────────────┼────────────┘
            │                        │                          │
┌───────────┼────────────────────────┼──────────────────────────┼────────────┐
│           ▼         HUB / ENSEMBLE LAYER                       ▼            │
│  ┌─────────────────────────────────────────────────────────────────────┐    │
│  │                      Submission Validator                           │    │
│  │  · Schema check (ISO week, quantile levels, horizon)                │    │
│  │  · Range plausibility (0-100% for positivity)                       │    │
│  │  · Monotonicity of quantiles                                        │    │
│  └────────────────────────────────┬────────────────────────────────────┘    │
│                                   ▼                                         │
│  ┌─────────────────────────────────────────────────────────────────────┐    │
│  │                  AWBE Ensemble Engine                               │    │
│  │  Adaptive Weight Blending Ensemble                                  │    │
│  │  · Sliding window WIS tracking (last N weeks)                       │    │
│  │  · Softmax weight solver                                            │    │
│  │  · Fallback to equal weights if N < min_history                     │    │
│  │  · Produces: ensemble quantile forecast + model weight table        │    │
│  └────────────────────────────────┬────────────────────────────────────┘    │
│                                   ▼                                         │
│  ┌─────────────────────────────────────────────────────────────────────┐    │
│  │                  Evaluation Engine                                  │    │
│  │  · WIS (primary), MAE, PI coverage                                  │    │
│  │  · Wave-stratified: winter peak / summer peak / trough              │    │
│  │  · Leave-one-season-out CV                                          │    │
│  │  · Benchmark comparison (historical percentile)                     │    │
│  └────────────────────────────────┬────────────────────────────────────┘    │
└───────────────────────────────────┼─────────────────────────────────────────┘
                                    │
┌───────────────────────────────────┼─────────────────────────────────────────┐
│                   DISTRIBUTION LAYER                                        │
│                                   ▼                                         │
│  ┌────────────────┐  ┌─────────────────────┐  ┌──────────────────────────┐  │
│  │  Public API    │  │  CHP Dashboard      │  │  Research Archive        │  │
│  │  (JSON/CSV)    │  │  (operational)      │  │  (GitHub + Zenodo)       │  │
│  │  Machine-read  │  │  · peak alerts       │  │  · versioned forecasts   │  │
│  │  · quantile    │  │  · severity signals  │  │  · evaluation scores     │  │
│  │    forecasts   │  │  · wave onset        │  │  · model metadata        │  │
│  └────────────────┘  └─────────────────────┘  └──────────────────────────┘  │
└─────────────────────────────────────────────────────────────────────────────┘

## 3.2  Key Interfaces and Data Contracts

| Interface | From → To | Format / Contract |
| --- | --- | --- |
| CHP data ingestion | CHP Flu Express PDF → Master Dataset | Automated PDF scraper; weekly batch; ISO 8601 dates; ILI rate per 1,000 + positivity % |
| FluNet pull | WHO FluNet API → Master Dataset | Weekly REST pull; columns: H1N1/H3N2/B counts, specimens, positivity by strain |
| HKO weather feed | HKO API/FTP → Master Dataset | Weekly actual AH (g/kg), temp (°C), RH (%); replaces climatological normals |
| Wastewater signal | HKWQAA / HKU EPD → Master Dataset | Weekly viral load (copies/mL); lag-adjusted; missing-value policy required |
| Model submission | Each model team → Hub validator | FluSight CSV: columns = forecast_date, target, horizon, type (quantile/point), quantile, value |
| Quantile levels | Models → Hub | 23 quantiles: 0.01,0.025,0.05,0.10,0.15,...,0.85,0.90,0.95,0.975,0.99 + point estimate |
| Forecast targets | Hub → Distribution | Primary: weekly lab positivity %; Secondary: GOPC ILI rate per 1,000; Horizons: 1-4 weeks |
| AWBE weight table | Ensemble engine → Archive | Weekly JSON: model_id, weight, rolling_WIS, n_obs_in_window |
| Public API response | Hub → External users | JSON: {forecast_date, target, horizon, quantiles: {0.01:..., 0.5:..., 0.99:...}} |

## 3.3  Module Dependencies

The dependency graph determines the sequencing of implementation. A module cannot be built until all its upstream dependencies are complete.

| Module | Depends On | Blocking For |
| --- | --- | --- |
| CHP ETL pipeline | CHP website access, PDF parser | All models, Master Dataset |
| Master Dataset schema v2 | CHP ETL, FluNet pull, HKO feed | All models, Ensemble engine |
| Target variable definition | CHP ETL, stakeholder agreement | All model training, Hub validator |
| SARIMA model (rebuilt) | Master Dataset, target definition | Ensemble, CV evaluation |
| ETS(A,A,A) (existing) | Master Dataset (RETAIN) | Ensemble (already works) |
| Gradient Boosting model | Master Dataset + novel streams | Ensemble, CV evaluation |
| Bootstrap quantile extractor | Any fitted model | FluSight-format submission, WIS scoring |
| Hub validator | Target definition, quantile spec | AWBE engine, evaluation |
| AWBE engine | Hub validator, WIS scoring, ≥3 models | Ensemble forecast output |
| WIS scoring | Quantile submissions, actuals | AWBE engine, evaluation reports |
| Wave-stratified evaluator | WIS scoring, wave detection logic | Seasonal performance reports |
| Public API | Hub validator, ensemble engine | CHP operational integration |
| CHP Dashboard | Public API, alert thresholds (agreed) | Operational deployment |

# 4. Implementation Roadmap

The roadmap is organised into five phases. Each phase has defined deliverables, duration estimates, and entry/exit criteria. Phases 0-2 can be executed by a single researcher; Phase 3 onwards requires institutional partnerships.

## Phase 0: Foundation Reconstruction (Weeks 1-4)

Phase Goal: Goal: Restore full reproducibility of the existing pipeline. Before any new feature is added, scripts 01-06 must be re-implemented so the pipeline can be re-run on any date with fresh data. This is non-negotiable — the project is currently not reproducible.

| Task | Effort | Output | Notes |
| --- | --- | --- | --- |
| Reconstruct script 01: data preparation | 3 days | 01_data_preparation.py (full) | Use existing outputs + README to reverse-engineer. Key: COVID flag logic, ILI+ formula, log-transform |
| Reconstruct script 02: stationarity tests | 1 day | 02_stationarity_acf_pacf.py (full) | ADF test, ACF/PACF at multiple lags, order selection grid |
| Reconstruct script 03: SARIMA fitting | 3 days | 03_model_fitting.py (full) | Must reproduce AIC=-1772.62; validate against model_coefficients.json |
| Reconstruct script 04: residual diagnostics | 1 day | 04_residual_diagnostics.py (full) | Ljung-Box, Shapiro-Wilk, 2x2 panel; match existing figures |
| Reconstruct script 05: forecast generation | 2 days | 05_forecast_generation.py (full) | Bootstrap n=500 draws; reproduce existing forecast_78wk_2026_27.csv |
| Reconstruct script 06: figures + narrative | 1 day | 06_figures_and_narrative.py (full) | Publication figures; validate against existing PNGs |
| Add quantile extraction to script 05 | 1 day | 23-quantile output per forecast step | Extract from bootstrap draws; test monotonicity |
| Implement WIS scoring function | 1 day | wis.py utility module | WIS = sum over quantile levels of interval scores; validate against FluSight reference |
| End-to-end pipeline test | 1 day | All outputs match existing CSVs/figures | Run scripts 01-08 sequentially; compare outputs |

Exit criterion: Running python 01_data_preparation.py ... python 08_ensemble_evaluation.py sequentially produces outputs that match (within floating-point tolerance) the committed CSVs and figures.

## Phase 1: Core Infrastructure (Weeks 5-14)

Phase Goal: Goal: Build the data infrastructure and hub skeleton that will support all future models. Agree on the formal target variable. Stand up the submission validator.

| Task | Effort | Output | Dependencies |
| --- | --- | --- | --- |
| Formal target variable definition | 1 week (workshop) | Signed-off target spec document | CHP stakeholder meeting; epidemiologist input |
| Automated CHP data ingestion (ETL) | 2 weeks | chp_etl.py: weekly scrape → master dataset | CHP website structure; PDF parser (pdfplumber or tabula) |
| FluNet API weekly pull | 3 days | flunet_pull.py: REST → appended to master | WHO FluNet public API |
| HKO actual weather feed | 3 days | hko_pull.py: observed AH/temp/RH → master | HKO open data API or FTP |
| Master Dataset schema v2 | 1 week | updated master_dataset_v2.csv + schema doc | All ETL scripts above |
| Hub submission validator | 1 week | validator.py: schema check, monotonicity, range | Target spec, quantile spec (FluSight) |
| FluSight-format submission wrapper | 3 days | submission_formatter.py for each model | Bootstrap quantile extractor (Phase 0) |
| School term calendar integration | 2 days | school_term_binary.py → feature in master | HK Education Bureau calendar (public) |
| Year-round forecasting window logic | 3 days | forecast_scheduler.py: weekly update, no season cutoff | Master dataset v2 |
| Git repository structure for hub | 2 days | hub/ directory with model-submissions/, ensemble/, api/ | Architecture design |

Exit criterion: Automated pipeline can ingest a new week of CHP + FluNet + HKO data, append to master dataset, and produce a valid FluSight-format submission from the existing SARIMA model, scored by WIS.

## Phase 2: Model Enhancement (Weeks 15-28)

Phase Goal: Goal: Expand the model ensemble from 3 homogeneous components to 3 intentionally diverse models. Integrate novel data streams. Implement AWBE. Conduct leave-one-season-out validation.

| Task | Effort | Output | Key Decisions |
| --- | --- | --- | --- |
| Bimodal seasonal SARIMA redesign | 2 weeks | SARIMA with two-regime seasonal structure or SARIMA(p,d,q)(P,D,Q)[26] for semi-annual cycle | Test S=26 vs S=52; compare bimodal AIC |
| Absolute humidity actual-data regressors | 1 week | Replace climatological normals with weekly HKO observed AH in SARIMA | Normalisation: rolling z-score vs fixed 30yr normals |
| Wastewater surveillance integration | 2 weeks | ww_model.py: lag analysis + feature for GB model | Data access agreement; lag optimisation (2-4 weeks) |
| Cross-border travel data integration | 1 week | travel_feature.py: HK-Mainland weekly passenger volume | IMMD or HKIA open data; handle COVID-era gap |
| Gradient Boosting model (Model C) | 2 weeks | gb_model.py: XGBoost/LightGBM + feature importance | Feature set: lagged ILI+, AH, travel, wastewater, school |
| AWBE implementation | 2 weeks | awbe.py: sliding-window WIS tracker + softmax weight solver | Window length N (recommend 8-12 weeks); min history threshold |
| Wave detection algorithm | 1 week | wave_detector.py: onset/peak/offset for winter+summer waves | Threshold: % above baseline; minimum duration |
| Wave-stratified evaluation | 1 week | wave_eval.py: WIS by wave type and season | Requires wave detector |
| Leave-one-season-out CV | 1 week | loso_cv.py: 5+ seasons, all models | Define 'season' for bimodal HK (recommend: Oct-Sep epi-year) |
| Strain adjustment: uncertainty-aware | 1 week | Probabilistic strain multiplier using FluNet strain distribution | Replace deterministic scalar with distribution-weighted adjustment |
| Performance benchmarking vs literature | 1 week | Comparison table vs published HK flu forecasting studies | Identify 3-5 published benchmarks with comparable metrics |

Exit criterion: Three diverse models producing validated FluSight-format quantile submissions, combined by AWBE, with wave-stratified WIS scores computed across ≥5 seasons of leave-one-out CV.

## Phase 3: Hub Architecture & Distribution (Weeks 29-42)

Phase Goal: Goal: Transform the single-researcher pipeline into a multi-institutional hub. Establish model submission protocol, public API, and operational dashboard. Onboard first external model contributor.

| Task | Effort | Output |
| --- | --- | --- |
| Hub specification document | 1 week | Formal model submission protocol; data dictionary; quantile spec; evaluation criteria |
| External model submission portal | 2 weeks | GitHub-based submission workflow (PR or API endpoint); automated validation on submission |
| Model metadata registry | 1 week | model_registry.json: model_id, institution, method, data_sources, contact |
| Public machine-readable API (v1) | 3 weeks | REST API: /forecasts, /scores, /models, /data; JSON + CSV; OpenAPI spec |
| CHP operational dashboard (prototype) | 2 weeks | Web dashboard: current ensemble forecast, peak alerts, wave status, WIS trend |
| First external model onboarding | 2 weeks | One HKU or CUHK team submitting model to hub; documented onboarding guide |
| Governance document v1 | 1 week | Terms of participation, data sharing, authorship policy, model acceptance criteria |
| Pilot evaluation report | 1 week | Assessment of first full season with multi-model hub |

## Phase 4: Governance, Sustainability & Operations (Weeks 43+)

| Task | Milestone |
| --- | --- |
| Formal CHP partnership agreement | Operational data sharing MOU; CHP integrated into governance board |
| RGC / ITF funding application | Grant application submitted; HK-FluEns as named deliverable |
| HKU School of Public Health hosting agreement | Server infrastructure; institutional review board alignment |
| Year 1 operational review | Annual assessment of model performance, data quality, and partner satisfaction |
| Journal publication: methods paper | Peer-reviewed methods paper describing HK-FluEns architecture, evaluation, and first-season results |
| APEC / WHO WPRO engagement | Present HK-FluEns as regional model for FluSight-style networks in Asia-Pacific |

## 4.1  Roadmap Summary Timeline

| Phase | Weeks | Key Deliverable | Status |
| --- | --- | --- | --- |
| Phase 0: Foundation | 1-4 | Scripts 01-06 reconstructed; WIS scoring; end-to-end test | START NOW |
| Phase 1: Core Infrastructure | 5-14 | Automated ETL; target agreed; hub skeleton; FluSight format | Requires Phase 0 |
| Phase 2: Model Enhancement | 15-28 | 3 diverse models; AWBE; wastewater; LOSO CV | Requires Phase 1 |
| Phase 3: Hub & Distribution | 29-42 | Public API; external contributor; CHP dashboard prototype | Requires Phase 2 |
| Phase 4: Governance | 43+ | CHP MOU; RGC grant; publications; APEC engagement | Parallel from Phase 3 |

# 5. Risk Assessment

The following risk register covers technical, data, institutional, and project risks. Each risk is rated by likelihood (1-3) and impact (1-3), giving a priority score of 1-9.

| Risk | Category | L | I | Score | Mitigation |
| --- | --- | --- | --- | --- | --- |
| CHP changes PDF format or website structure, breaking ETL pipeline | Data | 2 | 3 | 6 | Build ETL with format detection; maintain manual fallback; monitor CHP website; contact CHP for structured data agreement |
| COVID-era imputed data (MAPE 76.3%) biases model training | Technical | 3 | 2 | 6 | Run all models with and without imputed period; weight post-COVID data more heavily in AWBE; flag imputed weeks in all outputs |
| Bimodal seasonality not adequately captured by SARIMA(1,0,1)(1,1,0)[52] | Technical | 3 | 2 | 6 | Test SARIMA variants with S=26; evaluate two-regime models; ETS(A,A,A) partially compensates; monitor wave-stratified WIS |
| Target variable definition stalls due to CHP/academic disagreement | Institutional | 2 | 3 | 6 | Prepare 3 candidate targets with data availability analysis; schedule workshop in Phase 1 week 1; identify decision-maker |
| Wastewater data access not secured or lag structure unclear | Data | 2 | 2 | 4 | Begin data-sharing discussions immediately; design model to work without wastewater as optional feature; plan lag sensitivity analysis |
| No external model contributors join by Phase 3 | Institutional | 2 | 2 | 4 | Identify 2-3 potential contributors early (HKU, CUHK, PolyU); offer co-authorship incentive; build easy onboarding |
| Equal-weight ensemble performs better than AWBE (weight instability with few models) | Technical | 2 | 2 | 4 | Keep equal-weight ensemble as production fallback; AWBE requires minimum history; use regularised weight solver |
| Funding not secured; project depends on single researcher | Project | 2 | 3 | 6 | Submit RGC/ITF application in Phase 3; seek HKU startup funding; modular design enables partial delivery at each phase |
| WIS scores are dominated by PI width (wide intervals game the metric) | Technical | 2 | 2 | 4 | Track sharpness separately; require calibration check (empirical coverage at each quantile level); penalise systematically over-wide intervals |
| Structural break from post-COVID behaviour change (baseline shift) | Epidemiological | 2 | 2 | 4 | COVID suppression flags already in dataset; train SARIMA primarily on post-COVID data (2022+); monitor for level shift annually |
| HKO actual weather data not available in machine-readable form | Data | 1 | 2 | 2 | HKO provides open data portal; climatological normals are fallback; assess actual data quality before committing to regressors |
| Model-ready data format changes break downstream scripts | Technical | 2 | 2 | 4 | Version all data schemas; add schema validation step in ETL; pin column names in a constants.py file |

# 6. Open Decision Points

The following decisions must be made before or during Phase 1. Each is presented with the options, trade-offs, and a recommendation. Decisions marked BLOCKING cannot be deferred — they gate downstream implementation.

## Decision 1: Forecast Target Variable  [BLOCKING]

| Option | Definition | Pros | Cons |
| --- | --- | --- | --- |
| Option A (current) | ILI+ = GOPC ILI rate/1000 × lab positivity fraction | Already computed in master dataset; captures both clinical and virological signal | Not a standard WHO metric; hard to benchmark against international studies; near-zero values cause MAPE issues |
| Option B (preferred) | Weekly lab positivity % = positive specimens / total specimens tested | Direct FluSight analogue (wILI%); standard WHO FluNet metric; less susceptible to healthcare-seeking changes | Does not capture clinical severity; FluNet data may lag CHP by 1-2 weeks |
| Option C (secondary) | GOPC ILI rate per 1,000 consultations | Operationally relevant to CHP for resource planning; directly from CHP surveillance | Affected by non-flu respiratory illness; no international comparator |

Recommendation: Adopt Option B (lab positivity %) as the primary forecast target for FluSight compatibility, with Option C (GOPC ILI rate) as the mandatory secondary target for CHP operational relevance. Retire Option A as the primary target.

## Decision 2: Seasonal Structure for SARIMA  [Needed by Phase 2]

Hong Kong has a bimodal pattern. The current SARIMA uses S=52 (annual). Options: (A) retain S=52 with AH regressors as bimodal proxy; (B) use S=26 (semi-annual) to explicitly model two peaks; (C) fit separate winter and summer models; (D) use a regime-switching model with HMM or threshold detection.

Recommendation: Test S=52 vs S=26 empirically using the existing dataset (AIC/BIC comparison + wave-stratified CV). Parallel-develop Option C (separate season models) as it is the most interpretable approach for clinician communication. Decision gate: Phase 2, Week 15.

## Decision 3: AWBE Window Length  [Needed by Phase 2]

The AWBE sliding window N determines how quickly weights adapt to model performance changes. Short N (4-6 weeks) is highly responsive but noisy; long N (16-20 weeks) is stable but slow to adapt. Published Hong Kong AWBE literature (Chan et al.) uses N=8-12.

Recommendation: Use N=8 weeks as the default, with sensitivity analysis at N=4, 12, 20. Define a minimum history threshold of 2N weeks before AWBE activates (fall back to equal weights below threshold).

## Decision 4: COVID Imputation Handling in Model Training  [Needed by Phase 0]

The imputed COVID-gap series (Apr 2020-Sep 2022, MAPE 76.3%) inflates training data uncertainty. Options: (A) include imputed weeks with equal weight; (B) exclude imputed weeks entirely; (C) include but down-weight using inverse MAPE; (D) train two models (one with, one without) and compare.

Recommendation: Option D as the validation protocol; Option B as the production default. The post-COVID period (2022-present) has sufficient data for robust training, and introducing high-uncertainty imputed data adds more noise than signal for near-term forecasting.

## Decision 5: Wastewater Integration Architecture  [Needed by Phase 2]

Wastewater data can be used as: (A) a leading indicator feature in the gradient boosting model only; (B) a separate standalone model (wastewater-based SEIR); (C) a real-time data stream that updates all model priors. Options B and C require a data-sharing agreement and lag structure analysis.

Recommendation: Start with Option A (feature in GB model) as it has no additional infrastructure requirements. Commission a lag cross-correlation analysis between wastewater viral load and ILI+ with the first 4 weeks of wastewater data. Promote to Option B once lag structure is validated.

## Decision 6: Hub Hosting and Data Governance  [Needed by Phase 3]

Options for hub hosting: (A) GitHub Pages + static JSON (low cost, no server needed, limitations for real-time); (B) HKU server with REST API (requires HKU IT agreement); (C) cloud-hosted (AWS/GCP, requires funding). Governance: CHP must decide whether to formally endorse forecasts or receive them as research outputs only.

Recommendation: Phase 3 prototype uses Option A (GitHub + static JSON) for rapid deployment. Apply for HKU server access in parallel. Initiate CHP governance conversation in Phase 1 alongside the target variable workshop.

# 7. Immediate Next Steps (Phase 0 Start)

The following actions should be initiated immediately, in order, before any new feature development begins.

| # | Action | Owner | Deadline | Blocking For |
| --- | --- | --- | --- | --- |
| 1 | Reconstruct script 01 (data preparation) — highest priority stub | Parth Singh | Week 1 | All downstream scripts |
| 2 | Reconstruct scripts 02-06 sequentially, validating each output against committed CSVs | Parth Singh | Week 2-3 | Pipeline reproducibility |
| 3 | Add 23-quantile extraction to script 05 (from bootstrap draws) | Parth Singh | Week 3 | FluSight compatibility |
| 4 | Implement WIS scoring utility (wis.py) | Parth Singh | Week 3 | AWBE, evaluation |
| 5 | Schedule stakeholder workshop for target variable decision with supervisor/CHP contact | Parth Singh + Supervisor | Week 4 | Phase 1 ETL design |
| 6 | Assess CHP Flu Express website structure for PDF scraping feasibility | Parth Singh | Week 4 | ETL pipeline |
| 7 | Run full end-to-end pipeline test; document any discrepancies from committed outputs | Parth Singh | Week 4 | Phase 0 exit criterion |
| 8 | Create hub/ directory structure in version control with placeholder READMEs | Parth Singh | Week 4 | Phase 1 hub skeleton |

# Appendix A: FluSight Quantile Format Reference

All model submissions to HK-FluEns must follow the FluSight CSV format (adapted for Hong Kong targets).

forecast_date, target, horizon, type, quantile, value
2026-04-05, lab_positivity_pct, 1 wk ahead, quantile, 0.010, 3.2
2026-04-05, lab_positivity_pct, 1 wk ahead, quantile, 0.025, 4.1
...
2026-04-05, lab_positivity_pct, 1 wk ahead, quantile, 0.500, 12.5
...
2026-04-05, lab_positivity_pct, 1 wk ahead, quantile, 0.990, 31.8
2026-04-05, lab_positivity_pct, 1 wk ahead, point, NA, 12.5

Required quantile levels (23 total): 0.010, 0.025, 0.050, 0.100, 0.150, 0.200, 0.250, 0.300, 0.350, 0.400, 0.450, 0.500, 0.550, 0.600, 0.650, 0.700, 0.750, 0.800, 0.850, 0.900, 0.950, 0.975, 0.990. Plus one 'point' type row per horizon.

Targets: lab_positivity_pct (primary), gopc_ili_rate_per1000 (secondary). Horizons: 1 wk ahead, 2 wk ahead, 3 wk ahead, 4 wk ahead.

# Appendix B: Weighted Interval Score (WIS) Formula

WIS is the primary evaluation metric for HK-FluEns, consistent with FluSight. For a single forecast at quantile level α and observed value y:

IS_α(l, u) = (u - l) + (2/α)(l - y)[y < l] + (2/α)(y - u)[y > u]

WIS = (1/K) * Σ_α IS_α(l_α, u_α) + |y - point_forecast| / 2

where K = number of quantile intervals (11 symmetric intervals from α=0.02 to α=0.98)

WIS decomposes into: sharpness (average PI width), calibration (underprediction + overprediction penalties). A model with narrow, well-calibrated intervals achieves the lowest WIS. The AWBE re-weights models inversely proportional to their rolling WIS.

# Appendix C: AWBE Algorithm Sketch

# Pseudocode: Adaptive Weight Blending Ensemble
# N = sliding window length (e.g. 8 weeks)
# K = number of models

For each forecast date t:
  if t < t_start + 2*N:  # insufficient history
    weights = [1/K] * K  # equal weights
  else:
    wis = []  # collect recent WIS per model
    for model_k in models:
      wis_k = mean(WIS(model_k, t-N:t-1))  # rolling window
      wis.append(wis_k)
    # Inverse-WIS softmax
    inv_wis = [1 / (w + epsilon) for w in wis]
    weights = softmax(inv_wis)  # sum to 1
  ensemble_quantile_q = sum(w_k * model_k_quantile_q for k, w in zip(models, weights))
  log_weight_table(t, weights)

Note: Linear quantile pooling (weighted average of CDFs at each quantile level) is the recommended combination method, as it preserves the calibration properties of individual model distributions better than averaging point forecasts.

HK-FluEns Planning Document  |  March 2026  |  Parth Singh  |  Confidential — Planning Phase